## RMMP Risk Assessment
Ref | Task/Process | Environmental Aspect | Risk Source | Current Controls | L | C | R | WESP Heat Plant Improvement | L | C | R
[5 empty] | Residual Risk |  |  |  | Future Risk
RISK-0910 | Jet dryer | Air (aesthetics) | Potential for offensive odours to be emitted offsite, affecting neighbours. Odour originating from drying and combustion. | Monthly environmental inspection includes checking for offensive odours. Modelling in Ektimo report R007112-3 indicated medium risk of disamenity from odour at nearest neighbours. | B | 4 | H | Install abatement equipment (WESP ) to reduce Smoke/ Blue Haze which cause odour. | D | 4 | L
RISK-0911 | Drum dryer | Air (aesthetics) | Potential for offensive odours to be emitted offsite, affecting neighbours. Odour originating from drying and combustion. | Monthly environmental inspection includes checking for offensive odours. Modelling in Ektimo report R007112-3 indicated medium risk of disamenity from odour at nearest neighbours. | B | 4 | H | Install abatement equipment to reduce Smoke Blue Haze which cause odour. | D | 4 | L
RISK-0912 | Press 1, 2 & 3 | Air (aesthetics) | Potential for offensive odours to be emitted offsite, affecting neighbours. Odour originating from pressing particleboard. | Monthly environmental inspection includes checking for offensive odours. Modelling in Ektimo report R007112-3 indicated medium risk of disamenity from odour at nearest neighbours. | B | 4 | H | Install abatement equipment (WESP) to reduce smoke/ Blue Haze which causes odour. | E | 4 | L
RISK-0920 | Operation of Jet Dryer. | Air (toxicity) | Combustion of natural gas and saw dust produce carbon monoxide; potential licence exceedence. | Management of burner efficiency to minimise CO. Combustion, CO, CO2 and O2 checked as part of burner servicing, scheduled through Mainpac. Tested burner efficiency. Result was 86%. Hygienist and Air quality report conducted; SEPP AQM design criteria met, Air Quality Index = Very Good. | A | 4 | H | Re-test burner efficiency and implement operational controls to minimise CO such as improved oxygen levels. Install flue gas recirculation, or other technologies to reduce emissions. | D | 5 | L
RISK-0921 | Operation of Jet Dryer. | Air (toxicity) | Thermal generation of NOx during combustion of natural gas and saw dust; potential licence exceedence; minimal to nil effect on surrounding environment. | Management of burner efficiency to minimise NOx. Tested burner efficiency. Result was 86%. Hygienist and Air quality report conducted; SEPP AQM design criteria met, Air Quality Index = Very Good. | A | 4 | H | Re-test burner efficiency and implement operational controls to minimise NOx; e.g. via setting a maximum load of resinated recycled wood fuel. Install flue gas recirculation, or other technologies to reduce emissions. | C | 5 | L
RISK-0922 | Operation of Jet Dryer. | Air (toxicity) | Combustion of saw dust and drying of wood products produces particulates; minor off-site effects (nearest neighbour). | Cyclones installed downstream of dyer remove some particles from the flue gas. In-line monitoring of particulates flowing through stack; read-out and alarms to pressline operators. Hygienist and Air quality report conducted; SEPP AQM design criteria met for Total Suspended Solids, PM10 and PM 2.5; Air Quality Index = Good for PM 10 and PM 2.5. | A | 4 | H | Update combustion, temperature and load controls to mitigate VOCs and particle emissions. Install WESP to reduce particulate emissions. | C | 5 | L
RISK-0925 | Operation of Drum Dryer. | Air (toxicity) | Combustion of natural gas and saw dust produce carbon monoxide; potential licence exceedence; minimal to nil effect on surrounding environment. | Management of burner efficiency to minimise CO. Combustion, CO, CO2 and O2 checked as part of burner servicing, scheduled through Mainpac. Tested burner efficiency. Result was 86%. Hygienist and Air quality report conducted; SEPP AQM design criteria met, Air Quality Index = Very Good. | A | 4 | H | Re-test burner efficiency and implement operational controls to minimise CO. Optimise oxygen levels to reduce emissions. | D | 5 | L
RISK-0926 | Operation of Drum Dryer. | Air (toxicity) | Thermal generation of NOx during combustion of natural gas and saw dust; potential licence exceedence. | Management of burner efficiency to minimise NOx. Tested burner efficiency. Result was 86%. Hygienist and Air quality report conducted; SEPP AQM design criteria met, Air Quality Index = Very Good. | A | 4 | H | Implement operational controls to minimise NOx Model emissions to confirm absence of health impact. | D | 5 | L
RISK-0927 | Operation of Drum Dryer. | Air (toxicity) | Combustion of saw dust and drying of wood products produces particulates; minor off-site effects (nearest neighbour). | Cyclones installed downstream of dyer remove some particles from the flue gas. Maintenance and cleaning of drum and cyclones (B75W149c Drum Dryer Maintenance). In-line monitoring of particulates flowing through stack; read-out and alarms to pressline operators. Hygienist and Air quality report conducted; SEPP AQM design criteria met for Total Suspended Solids, PM10 and PM 2.5; Air Quality Index = Good for PM 10 and PM 2.5. | A | 4 | H | Install WESP to reduce particulate emissions. Add in a Heat Plant to re-use captured organic dust and produce energy. Emissions from Heat Plant sent to WESP. | C | 5 | L
RISK-0928 | Operation of Drum Dryer. | Air (toxicity) | VOCs are evapourated from wood during drying and from combustion of saw dust; potential licence exceedence. | Temperature and mass flow rate control of Jet and Drum dryers. | A | 5 | M | Install abatement equipment ( WESP) to reduce Blue Haze emissions. | C | 5 | L
RISK-0930 | Operation of Drum and Jet dryers. | Air (toxicity) | Formaldehyde released from wood material by heat from drying process, or from burning wood dust; potential licence exceedence from dryer stacks. | Formaldehyde resins used are E1, E0 and Super E0 types, which limit the amount of free frmaldehyde. Temperature control of presses. Temperature and mass flow rate control of Jet and Drum dryers. | A | 4 | H | Install abatement equipment (WESP) to reduce formaldehyde emissions. Model emissions to confirm acceptable health impact risk | C | 5 | L
RISK-0932 | Operation of Drum and Jet dryers. | Air (aesthetics) | Visible emissions (smoke, blue haze) released from dryer stacks, resulting in community complaints and potential licence exceedence. Note: Visible emissions are caused by VOCs and particulates, so compliance with VOC and Particulate limits extrapolates to compliance with L1_DA2. | Temperature control of presses. Temperature and mass flow rate control of Jet and Drum dryers. Maintenance and cleaning of drum and cyclones (B75W149c Drum Dryer Maintenance). Pressline operators can reduce burning of dust if required. | A | 4 | H | Install abatement equipment (WESP) to reduce visible emissions. | D | 5 | L
RISK-2101 | Proposed Heat Plant | Air (aesthetics) | Smoke - start up. | N/A - future improvement. |  |  |  | Interlock with WESP operability. Flue gas vents via dryer to WESP to remove particles, smoke. | D | 5 | L
RISK-2102 | Proposed Heat Plant | Air (aesthetics) | Smoke - operation. | N/A - future improvement. |  |  |  | Interlock with WESP operability. Flue gas vents via dryer to WESP to remove particles, smoke. | D | 5 | L
RISK-2103 | Proposed Heat Plant | Air (aesthetics) | Smoke - emergency venting. | N/A - future improvement. |  |  |  | Emergency vent coupled with alarm to shut down. Direct vent to WESP if practicable, unless required to prevent over-pressure and rupture. | E | 3 | L
RISK-2104 | Proposed Heat Plant | Air (toxicity) | Combustion byproducts - NOx CO | N/A - future improvement. |  |  |  | PLC control of combustion, fuel delivery rate, temperature and pressure to optimise combustion and minimise NOx and CO. Reciprocating grate to mix fuel and optimise burn. Secondary air to lower NOx. | C | 5 | L
RISK-2105 | Proposed Heat Plant | Air (toxicity) | Fine Particles PM10, PM2.5 | N/A - future improvement. |  |  |  | Interlock with WESP operability. Flue gas vents via dryer to WESP to remove particles. | D | 5 | L
RISK-2106 | Proposed Heat Plant | Air (toxicity) | VOCs trace | N/A - future improvement. |  |  |  | Combustion secondary chamber minimises potential for unburned VOCs | D | 5 | L
RISK-2107 | Proposed Heat Plant | Air (climate change) | CO2 emissions | N/A - future improvement. |  |  |  | On site re-use negates transport emissions and off-sets against landfill methane. PB production (cradle to gate) s CO2 negative and more than off-sets CO2 from heat plant. | E | 5 | L
RISK-2201 | Proposed WESP | Air (aesthetics) | Smoke/ Blue Haze - start up, | N/A - future improvement. |  |  |  | Dryers interlocks with WESP operability. WESP treats smoke/blue haze. | E | 4 | L
RISK-2202 | Proposed WESP | Air (aesthetics) | Smoke/ Blue Haze - operation | N/A - future improvement. |  |  |  | Dryers interlocks with WESP operability. WESP treats smoke/blue haze. Automatic PLC control of WESP process to ensure performance guarantee is met. Work instruction - operation of WESP, scrubber water replenishment. | D | 4 | L
RISK-2203 | Proposed WESP | Air (aesthetics) | Smoke/ Blue Haze - upset conditions | N/A - future improvement. |  |  |  | Daily electrode cleaning of ESP. Visual monitoring of emissions daily. Preventative maintenance schedule as per manufacturers specification, and added into PM system. Annual stack test to confirm low particles and odour risk. | D | 4 | L
RISK-2204 | Proposed WESP | Air (toxicity) | Fine Particles PM10, PM2.5 | N/A - future improvement. |  |  |  | Daily electrode cleaning of ESP. Visual monitoring of emissions daily. Preventative maintenance schedule as per manufacturers specification, and added into PM system. Annual stack test to confirm low particles and odour risk. | D | 4 | L
RISK-2205 | Proposed WESP | Air (toxicity) | VOCs trace | N/A - future improvement. |  |  |  | Daily electrode cleaning of ESP. Visual monitoring of emissions daily. Preventative maintenance schedule as per manufacturers specification, and added into PM system. Annual stack test to confirm low particles and VOC risk. | D | 5 | L
RISK-2207 | Proposed WESP | Air (climate change) | Electrical energy use - Scope 2 CO2 emissions | N/A - future improvement. |  |  |  | Balance between energy use in WESP and best practice air emissions control ex-dryers. Particleboard manufacture has a low carbon footprint if carbon storage is included in the calculations (production is actually negative). With site energy recovery an emisison rate of approx. 8 - 9 kg CO2-eq per m2 is estimated (ref. EPD Australiasia declaration in accordance with ISO 14025, Wood Solutions, 2015. | C | 4 | L

## Matrix
RISK MATRIX |  | CONSEQUENCE (C) |  |  |  |  | CONSEQUENCE | Category |  | OHS | Environment | Quality | Business Continuity | Hierarchy of Controls
|  | Insignificant | Minor | Moderate | Major | Catastrophic |  | 1 | Catastrophic | Fatality. | High toxicity; regional impact; persistent environmental damage. | Complete loss of market share. | Loss of site.
LIKELIHOOD (L) |  | 5 | 4 | 3 | 2 | 1 |  | 2 | Major | Disabling/ permanent injury. | Large pollutant release; Toxic; Large area affected; Serious long term environmental damage. | Loss of major customers, multiple customers. | Total loss of production line.
Almost Certain | A | M | H | E | E | E |  | 3 | Moderate | MTI/LTI. | Significant off-site impacts; Low to medium toxicity. Serious medium term environmental damage. | Loss of a customer. | Significant loss of production; > 1 week.
Likely | B | M | H | H | E | E |  | 4 | Minor | FAI. | Moderate on-site, but minimal off-site impacts; Low toxicity; Short term environmental damage. | Short term loss of customer or sale. | Loss of production; > 1 day.
Possible | C | L | M | H | H | E |  | 5 | Insignificant | No treatment required. | Pollutant contained to small area; No off-site release; Nil to low toxicity; Nil to minor / temporary harm to environment. | Customer complaint. | Temporary loss, or delay; < 1 day.
Unlikely | D | L | L | M | H | H | LIKELIHOOD | Category |  | Guidance
Rare | E | L | L | L | M | M |  | A | Almost Certain | >80% chance; risk is expected in most circumstances.
Extreme/High: Unacceptable risk. Do not proceed until risk is reduced. | [7 empty] | B | Likely | 50-80% chance; risk is probable during normal operations.
Medium: Acceptable risk, but should be reduced if practicable. | [7 empty] | C | Possible | 10-50% chance; risk could occur during normal operations.
Low: Acceptable risk. | [7 empty] | D | Unlikely | 1-10% chance; risk could occur in an unusual set of circumstances.
[8 empty] | E | Rare | <1% chance; risk will almost never occur.
Hierarchy of Controls