# Restorative project order project plan

Contents

1.	Contact and reference information	2

2.	Project description	2

3.	Project delivery	5

4.	Project oversight	6

5.	Project reporting	6

6.	Stakeholder analysis	7

7.	Project budget	8

8.	Project risks and issues	12

9.	Submitting your plan	13

# Contact and reference information

| Your name: |  |
| --- | --- |
| Organisation name: |  |
| Your title/position in the organisation: |  |
| Postal address: |  |
| Email: |  |
| Daytime phone number: |  |
| Are you an incorporated group or a legal entity? (Yes/No, see below) |  |
| If you are not an incorporated group or a legal entity, which group or organisation can you partner with that is? |  |
| Do you have public liability insurance? (Yes/No) |  |
| Have you managed projects with funds of $30,000 or more? (Yes/No) |  |
| Which partner organisation(s) have you worked with in the delivery of environmental projects? Please list financial or in-kind project partners. |  |
| Do you have delegated authority to represent this project? (Yes/No) |  |
| Signature: | __________________________________________ |

# Project description

## Problem statement and solution summary

Provide a description of the issue that your project will address.

- Include information about the context, issue(s) or problem.

- Consider what the project will deliver that is restorative to the environment and / or the community.

The project does not have to directly relate to the circumstances of the offence for which the restorative project order has been made.

## Project scope

Clearly state what is and isn’t included in the project scope.

- Be as descriptive and specific as possible.

- Highlight any known variables.

Activities or deliverables that will be produced by other agencies or projects should be described as out-of-scope and included as dependencies at section 2.2.

| In scope |  |
| --- | --- |
| Out of scope |  |

## Project deliverables

The next 3 sections request information on the project output/deliverables, outcomes and benefits. These relate to each other as follows:

|  | Output/deliverable | Outcome | Benefit |
| --- | --- | --- | --- |
| Example: | Data management system implemented | Staff have faster access to information | Reduction in time spent searching for information |

Clearly specify the project outputs/deliverables. Consider how these will lead to project outcomes and benefits.

## Project outcomes

Specify the project outcomes and how they will be measured.

## Project benefits

List the project benefits.

The benefits are the measure of success of the project. Each benefit is a measurable change or improvement that is achieved because of what the project has delivered.

# Project delivery

## Project key phases and milestones

Clearly describe the key phases of work and their milestones. This sets out how the project intends to deliver the scope and deliverables of the project. Make reference the deliverables set out in section 1.3.

Note. This can be a summary. A full schedule will also be required as an Appendix.

| Phase | Start date | End date | Milestone(s) | Delivery date |
| --- | --- | --- | --- | --- |
| e.g Planning | 01/07/2025 | 30/10/2025 | Options analysis paper completed | 20/10/2025 |
| e.g Phase 1 | 1/11/2025 | 1/01/2026 | Guidance published on EPA website Pilot service delivered to users for testing | 05/05/2026 01/03/2026 |
| e.g Phase 2 | 02/02/2026 | 31/03/2026 | Pilot tool enhanced for external EPA users | 31/03/2026 |
| e.g Implementation | 01/04/2026 | 30/06/2026 | New enhanced tool provided to EPA users | 30/06/2026 |
| e.g Closure | 01/07/2026 | 01/09/2026 | Lessons learnt workshop completed Closure report completed | 16/7/2026 10/08/2026 |

## Dependencies

If your project requires external input or requirements, detail them below.

# Project oversight

Project oversight is an important function to reduce risk and streamline the delivery of project activities.

The level of oversight required depends on the specifics of the project. All projects must establish some form of project governance to support project delivery that is appropriate for the complexity of the project.

# Project reporting

Outline how you will report on your project, how often and in what format.

Reporting should:

- happen at agreed regular intervals (milestones)

- include a progress update

- identify any risks in delivery and outcomes.

All projects must provide a closure report at the conclusion of the project.

| # | Reported by | To whom | Reporting requirements | Frequency | Proposed Format |
| --- | --- | --- | --- | --- | --- |
| Example | Project manager | EPA project contact | Progress report | Monthly | Word document |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |

# Stakeholder analysis

Conducting a stakeholder analysis process is essential to understand who is impacted and/or interested in your project.

- Interest means: how important is the project to the stakeholder?

- Impact means: how much will the project impact on the stakeholders/community members?

Assess your stakeholders in the matrix below. Make sure you consider all stakeholders.

|  | Low interest | High interest |
| --- | --- | --- |
| High impact | Raise their understanding of the project and actively support their involvement. E.g. Local businesses | Engage actively with these stakeholders E.g. Local environment groups, residents impacted by pollution |
| Low impact | Consider informing these stakeholders. E.g. Wider community | Raise their understanding of the project and keep them in the loop. E.g. Local government, relevant environmental scientists |

# Project budget

Outline the project budget using the tables below. Add rows or columns as needed.

## Total Project Budget (ex. GST)

| Cost category | FY 2025/26 | FY 2026/7 | Total |
| --- | --- | --- | --- |
|  | Amount | Amount |  |
| Salaries & Wages | e.g. $150,000 | e.g. $150,000 | e.g. $300,000 |
| OPEX (e.g. consultants, contractors, licences) | e.g. $250,000 | e.g. $250,000 | e.g. $500,000 |
| CAPEX (e.g. hardware, software) | eg $50,000 | eg $50,000 | e.g. $100,000 |
| Contingency |  |  |  |
| Total budget |  |  |  |

## Project budget forecast break-down by month (ex. GST)

Add more tables to cover the full duration of the project.

### 2025-26

| Budget Category | OPEX category | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAPEX | - |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OPEX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Salary | - |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### 2026-27

| Budget Category | OPEX category | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAPEX | - |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OPEX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Salary | - |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Project budget forecast break-down by delivery component (ex. GST)

Provide a full breakdown of all project costs, resources, assets and any other costs incurred by the project per financial year.

| WRef | Key Component | Resource Type | Unit of Measure | Cost Type | FY 2025/6 | FY 2026/7 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | e.g. Project Management resource | Staff | 0.6 FTE | Salaries | e.g. $50,000 | e.g. $50,000 | e.g. $100,000 |
| 2 | e.g. Tree planting | Contractor (s) | 2 (contracts) | OPEX | e.g. $0 | e.g. $100,000 | e.g. $100,000 |
| 3 | e.g. Plants | - | 1 | CAPEX | e.g. $0 | e.g. $50,000 | e.g. $50,000 |
|  |  |  |  | Total | e.g. $50,000 | e.g. $200,00 | e.g. $250,000 |

## Anticipated procurement (If required)

Provide a summary of the projects procurement requirements. Include related activities, and the supporting management approach. Examples may include hiring a contractor, purchase of product, vendor engagement, etc.

Add columns or rows to this table to meet your project needs.

|  | Procurement 1 | Procurement 2 | Procurement 3 |
| --- | --- | --- | --- |
| Product or services required |  |  |  |
| Value of procurement |  |  |  |
| Procurement approach |  |  |  |

# Project risks and issues

## Risks

A project risk is an event or condition that, if it occurs, could impact the project’s objectives.

List all known risks below and add the associated impact and mitigation strategy.

| Risk | Impact | Mitigation plan |
| --- | --- | --- |
| Example: A key supplier might go out of business during the project. | This could delay delivery of critical components. | Identify alternative suppliers in advance. |

## Issues

A project issue is a current problem that is already affecting the project. Issues require immediate attention and resolution.

List all current issues below and add the associated impact and resolution that will be actioned.

| Risk | Impact | Resolution |
| --- | --- | --- |
| Example: The project’s lead developer has resigned unexpectedly. | Immediate disruption to the development schedule. | Reassign tasks and begin hiring a replacement. |

# Submitting your plan

Email your completed plan to restorative@epavic.gov.au.